Shillington & Stondon Federation of Lower Schools – Climate Action Plan

1 Year Plan Autumn 2025 – 2026

Designated Sustainability Lead: Sarah Woodham

Supported by: Ciara Dumpleton, Pam Buckle, Lynnette Mossop, Sustainability-link Governor (TBC)

| DECARBONISATION & ENERGY EFFICIENCY |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| ACTION |  | TIMEFRAME | STAKEHOLDERS | NOTES | PROGRESS TRACKER |
| Calculate baseline carbon footprint - To enable monitoring and tracking of any improvements over time. |  | Feb 2026 | Pam Buckle | Possible methods: - Complete the (Barkers) Sustainability Self-Assessment (free) (10 mins only) - www.barker-associates.co.uk - “Count your carbon” (Let’s Go Zero) - https://letsgozero.org - Carbon calculator – https://www.eco-schools.org.uk/count-your-carbon/ | - To start |
| Electricity: - LED lighting installed at Stondon, plus movement sensors for turning off lights. - New windows installed at Stondon and Shillington promoting carbon efficiency - New boiler and roof installed at Shillington promoting carbon efficiency - Deploy “winter/summer” and “Holiday” mode on boilers at each school to minimise wastage - Implement Beds Borough energy walkaround checklist – https://www.bedford.gov.uk/environmental-issues/sustainability/energy-and-water-advice-schools |  | Dec 2025 | PB |  | - Completed - Completed - Complete - Completed - Ongoing |
| Printing: - Introduce new supplier uses less ink/more eco-friendly |  | April 2026 | PB | New printer contracts in progress | - Underway |
| Transport: - Continue to conduct pupil/staff commute audit - Run bike-ability course annually at both schools - Use “Walk to School Week” and “Walk, Wheel, Cycle Trust” at both schools to promote awareness of environmental issues to children and parents |  | Oct 2025 June 2026 May 2026 | 2 x Heads |  | - Completed - Scheduled - Scheduled |
| Waste: - recycling boxes deployed in all classrooms - Promote use of compost heap (Shillington) with Yr 4 leading |  | Sept 2025 May 2026 | LM | On-going issue with food waste collection at Shillington (no current availability) | - Completed - To start |
| Uniform: - School uniform requirements reduced to a minimum (and no branded requirements) - Continue to make available and promote 2nd hand usage under sustainability banner (PTA, Shillington; School Office, Stondon) |  | Sept 2025 |  |  | - Completed - Ongoing |
| School Meals: - Use local fruit and veg (GM Growers) to reduce food miles |  | Sept 2025 |  |  | - Ongoing |
| ADAPTATION AND RESILIENCE |  |  |  |  |  |
| ACTION | TIMEFRAME |  | STAKEHOLDERS | NOTES | TRACKER |
| Water Usage: - Anglian Water – help with audit using Year 4 and possible assembly; | June 2026 |  | LM | LM to investigate Summer term: https://forms.office.com/e/wg27zb3cyt Richard Park rPark@anglianwater.co.uk Pam to check whether water usage at schools is currently metered. | - To start |
| Heat management: - Maintain shaded outdoor areas at Shillington; investigate options at Stondon - Audit where blinds not currently fit for purpose, so can prioritise when funding allows. | June 2026 |  | PB |  | - To start - To start |
| CULTURE & CURRICULUM, |  |  |  |  |  |
| ACTION | TIMEFRAME |  | STAKEHOLDERS | NOTES | TRACKER |
| Curriculum: Audit by Subject leads to consider where sustainability/biodiversity currently covered in curriculum and options to include | Sept 2026 |  | LM / All Subject Leads | Time to be allocated in staff meeting for staff to consider and investigate additional available resources Opportunities specifically for Science, Geography, English (texts) Free resources from: - https://letsgozero.org - National Education Nature Park - Sustainability Support for Education BE Green Boxes (available from Shefford & Flitwick Library) – games/resources/activities https://www.centralbedfordshire.gov.uk/xfp/form/467 | To start |
| School Policies: as these are updated/reviewed ALL should consider sustainability … particularly: - Mental Health & Wellbeing Policy - School Vision & Aims: 3 year plan | March 2026 Nov 2025 |  | CD/ All Governors |  | To start |